## Sheet1
Task No | TASKs | ESTIMATE | PRIORITY | DEVELOPER | STATUS | DEPENDENCIES
INFRASTRUCTURE MODULE
| Master page |  | 2 | Pavel | Pending |  | HTML coding is required
| Index page (admin desktop home page after login) |  | 2 | Pavel | Pending (Currently we use page generated with VS2010) |  | HTML coding is required
TEMPLATE MODULE
| Object model, storage organization. Template repository |  | 1 | Pavel | InProgress
| Template descriptor creation 1. Develop file format 2. Object model for xml parsing |  | 1 | Pavel | Pending
| Test template package creation based on existing gallery As a result we must get package with xlst(rule) & xml(descriptor). This template will be used for testing |  | 1 | Yura | Pending
| ZIP lib investigation. Helpers to work with ZIP |  | 1 | Yura | Pending
| File uploader 1. Integration with flex 2. Template package uploading (this logic is depens on repository logic to register template in the system) |  | 1 | Yura | InProgress
| Template management web page 1. Template management 2. Template uploading |  | 3 | Yura | Pending |  | HTML coding is required
CURATED GALLERY MODULE
| Curated gallery environment 1. Working with file system, gallery output organization 2. Configuration section to set environment settings |  | 1 | Pavel | InProgress
| Curated gallery creation 1. BL, put into storage, organize file system for gallery 2. Web page |  | 1 | ? | Pending
| Curated gallery management web page 1. Delete, activate/deactivate 2. gallery grid |  | 2 | ? | Pending |  | HTML coding is required
| Curated gallery preview page |  | 1 | ? | Pending |  | HTML coding is required
| Download curated galleru as archive |  | 2 |  | Pending
png file generation
Image web api
USER MODULE
| Basic admin user management 1. Storage organization, user object model, admin user repository base logic 2. Login/logout login in repository, forms authentication + login page |  | 1 | Pavel | Done (html codding required) |  | HTML coding is required
| Predefined admin user registration. Add user registration in post deployment script (via sql). |  | 1 | Pavel | Done
| Add admin user registration in repository 1. We must have server logic for user registration. This logic will be used in data importer project. This approach provide way not to implement UI logic for site content creation (this way will be used to load template packages and so on) 2. Web page |  | 2 | Yura | Pending (it partially has been done) |  | HTML coding is required
| Admin user management web page 1. Super admin can register or delete admins 2. activate/deactivate regular admins 3. ... |  | 3 | ? | Pending |  | HTML coding is required
DATA IMPORTER MODULE
| Data importer project organization |  |  | Pavel | Done
| Admin user import Admin users must be created based on xml files. Data importer uses real repository to register users in the system |  | 1 | Yura | Pending
| Template data import This task is depens on |  | 1 | Yura | Pending